## Bike Committee Minutes

## Associated Students

Wed, 2018.10.17, Nati Conference Room

CALL TO ORDER (12:32) by (Golay), minutes recorded by (Golay)

- ATTENDANCE

| Name | Note: | Name | Note: |
| --- | --- | --- | --- |
| Annie Golay Chair | Present | (vacant) Outreach Coordinator |  |
| Jacky Tang Vice Chair | Present | Jason McDaniel Project Coordinator | Present |
| (vacant) Administrative Coordinator |  | Sarah Siedschlag Advisor | Present |
| Thomas Eckman Graduate Representative | Present |  |  |

MOTION/SECOND: (Golay)/(McDaniel)

Motion language: Motion to approve attendance.

ACTION: Consent

Additional approval required: YES (Senate)

- COMMITTEE BUSINESS

- Approval of Minutes

MOTION/SECOND: (Golay)/(McDaniel)

Motion language: Motion to approve last week’s minutes.

ACTION: Consent

Additional approval required: YES (Senate)

- Approval of Agenda

MOTION/SECOND: (Golay)/(McDaniel)

Motion language: Motion to approve this week’s agenda.

ACTION: Consent

Additional approval required: YES (Senate)

- INDIVIDUAL REPORTS

  - Chair

- (comment 1)

- (comment 2)

  - Vice Chair

- (comment 1)

- (comment 2)

  - Administrative Coordinator

- (comment 1)

- (comment 2)

  - Project Coordinator

- (comment 1)

- (comment 2)

  - Outreach Coordinator

- (comment 1)

- (comment 2)

  - Advisor

- Last week, went to a meeting about the Byrd scooters on campus, which aren’t allowed because of the vehicle code on campus

- The campus policy office is trying to get more students aware of this issue

- UCSB is trying to get Byrd to make UCSB a red zone

- A UC-wide initiative has been proposed

- Transportation meeting in Ellison 4824 at 1pm

- PROJECT UPDATES

  - Bren Hall Lot

- Minor cap approved

- Moved on to the campus planning committee agenda, represented by Vice Chancellor Margaret Klawuun

- Optimistic project completion Summer 2019

  - IV Theater Bike Lot

- Through TPS, there will be restriping

- Anticipated completion would be during Spring Break

- Moving forward with reracking of this lot; need an estimate from peak racks; 12ft x 9ft; 20% more slots

  - Cheadle Hall bike path detour

- Oct. 15-28 closure

- Proceeding very rapidly

- DISCUSSION

  - Recruitment

- Interviews scheduled for this Friday at 11am and 12pm

  - Ridaround

- Proposed Route: Meet at flagpole outside of Cheadle; go down South Hall Lot to main bike path to IV to San Clemente and back to Cheadle.

- Thursday, October 18 from 4pm-5pm meet at the flagpole in front of Cheadle

- Problematic spots:

  - Stretch from the bike shop to the bus loop

  - Stretch near Rob Gym and at SAASB

- Visit proposed lecture hall site on the roundabout

  - Update on CSO Bike Sale

- Bike Sale on Saturday, October 20 from 12pm-5pm behind the police station in Lot 32

- Bike Committee tabling 12pm-2pm with the Bike Map (stickers, feedback, & water bottles)

- Working on where the Bike Committee should be tabling

  - Post CSO Bike Sale Advertisements in Free and For Sale

  - Print fliers for CSO bike sale and give to OSL office and around campus

  - Park in Lot 31--drive over table and tabling supplies

  - Bike Light Giveaway

- November 15 from 5pm-7pm at the Pardall Center

- Work on getting CSO recruits to help pass out the lights

- Working on confirmation to get CSOs

- Officer Stern wants to be there

  - New lecture hall currently planned for SE of Library, 2000+ seats

- Working on a letter

  - Address the later to the Chancellor or Vice Chancellor

    - Advised to send to the Chancellor

- Footprint of the building is approximately 27,600 square feet

- Alternative plan breaks lot into two and allows larger bike circle by moving building further west

- Demolition of Building 408, relocating the existing bike path

- 1,930 bicycle spaces will be available and replace those removed as part of construction and for the proposed classroom building

- Taking away 900 and adding 2000 bike parking

- They’re designing the building right now

  - “No biking,” “no scooters,” and “no skateboarding” signs around campus

- How to make signs more visible

- Improving signage in the Arbor and obtaining a new sign by SSMS

- Potential other locations:

  - Pardall Tunnel

- Pardall (more about no skateboarding through the tunnel)

- SSMS (“no biking”) & the Arbor (“no skateboarding”)

- Skateboarding is meant to only be on sidewalks

- *Ask Chelsea to make new signs

- Ask Officer Stern what he wants on the signs, locations, and who made them

  - Bike abatement shift on weekends

- CSOs would like the committee’s help

- Matt Bowman has a plan

ADJOURNMENT AT (1:10pm)