## Coastal Fund Minutes

## Associated Students

July 1, 2022, Email vote

CALL TO ORDER:  July 1, 2022,  minutes recorded by Kathryn

- ATTENDANCE

| Name | Note: absent (excused/not excused) arrived late (time) departed early (time) | Name | Note: absent (excused/not excused) arrived late (time) departed early (time) |
| --- | --- | --- | --- |
| Anannya Deshmukh Chair | present | Visala Tallavarjula Outreach Coordinator | present |
| Mykala Listorti Undergraduate Rep | present | Kathryn Bozanich Administrative Assist | present |
| Allison Daymond Undergraduate Rep | present | N/A Administrative Assist | present |
| Elizabeth Garabedian Undergraduate Rep | present | Sarah Siedschlag Advisor | present |
| Chloe Jenniches Undergraduate Rep | present | N/A Senate Liaison | N/A |
| Virginia Pan Graduate Student Rep | present | N/A Senate Liaison Proxy | N/A |
| Michaela Sten Graduate Student Rep | present |  |  |

B.   NEW BUSINESS

- Extension Request for CF-202111-01257

Jen Martin on 6/23/2022 at 7:23 AM:

I am writing to you and the Coastal Fund, as instructed, to request an extension to the end of the month (June 2022) to complete our work as outlined in our original proposal. Unfortunately, we encountered some unexpected challenges in our work and scheduling. We are still planning to submit a manuscript to the journal Marine Policy based on our research into the public comments gathered by the Office of National Marine Sanctuaries from the summer of 2020 through the winter of 2022.

- Initial approved end date: 5/31/2022

- Requested end date: 6/30/2022 (Sarah suggests 9/30/2022)

MOTION/SECOND: Anannya/Mykala

Motion language: Motion to approve extension request for CF-202111-01257 until September 30th, 2022

ACTION: Vote 6-0-1, Motion passes

Additional approval required: YES (Senate)

- Extension Request for CF-202201-01424

Stephanie Lucero on 6/27/2022 at 2:32 PM:

My start date was March 14, 2022 and my proposed end date was June 30, 2022. I would like to extend the end date to September 16, 2022.

The undergrads and I were successful in learning how to use the machine to collect light curve data and we ran numerous trials to solidify our methods. We also learned how to download and process the data and completed data processing for all of our practice trials. Completing the project by the end of June, however, was optimistic.

With our methods solidified, we now have a schedule for data collection and plan to have all data collected by July 2022. In August we will process data and figure out statistical methods for our results.  In September we will wrap up data analysis and write our Final Report.

- Initial approved end date: 6/30/2022

- Requested end date: 9/30/2022

MOTION/SECOND: Anannya/Mykala

Motion language: Motion to approve extension request for CF-202201-01424 until September 30th, 2022

ACTION: Vote 7-0-0, Motion passes

Additional approval required: YES (Senate)

- Extension Request for CF-202201-01422

Joanna Tang

- This project involved a new eDNA procedure that needed more time than expected to troubleshoot and work with. This has meant figuring out how to extract DNA, what primer to use, and processing full genomes from known samples since they are missing a good genome library.

- Additionally, their lab does not have access to the necessary technology for DNA extraction or PCR amplification, so they needed to devote a lot of time last quarter to coordinate with other labs.

- They have just started to make good progress, but will need an extension throughout the fall quarter. Their plan for summer is to continue DNA extractions and PCR amplification, and in fall, will complete sequencing and data analysis.

- Initial approved end date: 6/30/2022

- Requested end date: 12/31/2022

MOTION/SECOND: Anannya/Mykala

Motion language: Motion to approve extension request for CF-202201-01422 until December 31st, 2022

ACTION: Vote 6-0-1, Motion passes

Additional approval required: YES (Senate)

- Extension Request for WIN 21-19:

Mari Irving on 7/5/2022 at 3:38 PM:

I would like to request an extension for my minor coastal fund grant "Developing methods to detect the protozoan parasite Ophryocystis elektroscirrha in coastal monarch populations.” I’ve been held up in my spore collection efforts, but am now using Santa Barbara Natural History Museum’s collection and can proceed.

- Initial approved end date: 9/30/2022

- Requested end date: 12/31/2022

MOTION/SECOND: Anannya/Mykala

Motion language: Motion to approve extension request for WIN 21-19 until December 31st, 2022

ACTION: Vote 6-0-1, Motion passes

Additional approval required: YES (Senate)

- Reallocation Request for CF-202110-00351:

Mari Irving on 7/5/2022 at 3:38 PM:

Can I also reallocate $261.30 from my coastal fund grant CF-202110-00351 to pay my undergraduate intern Jessica Sofian?

MOTION/SECOND: Anannya/Mykala

Motion language: Motion to approve reallocation request for CF-202110-00351

ACTION: Vote 4-0-3, Motion passes

Additional approval required: YES (Senate)

ADJOURNMENT:

MOTION/SECOND: Email vote

Motion language: Motion to adjourn on July 11, 2022 at 8:42 PM

ACTION: Consent

Additional approval required: NO